## Week #1
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
2/4/2017 8:00 PM to 8:30 PM | Nikhil Nere | yes | Read and understand the project req | 2017-02-07 | 2017-02-09 | Every team member should get the clear understanding of the requiment from the domain and technology perspective.
Agenda : The first meeting was to understand each team member and their area of expertise | Ashish Deshpande | yes | Read and understand the project req | 2017-02-06 | 2017-02-08
| Aditya Kale | yes | Read and understand the project req | 2017-02-07 | 2017-02-09
| Avinash Singh | yes | Read and understand the project req | 2017-02-06 | 2017-02-08
| Ashwin Chati | yes | Read and understand the project req | 2017-02-06 | 2017-02-08

## Week #2
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
2/11/2017 8:00 PM to 8:30 PM | Nikhil Nere | yes | Understand the health domain Find data sources Analyze the datasets avaialble Follow up with TA if we can use An | 2017-02-13 | 2017-02-17 | Assumption that we can use data from different datasources
Agenda: Discuss the reuirement understandings and divide first set of tasks | Ashish Deshpande | yes | Requirements analysis for Dashboard UI Req for representing data on the UI | 2017-02-13 | 2017-02-16
| Aditya Kale | yes | Find technology solutions for Dashboard Explore JavaScript libraries that help to represent statitical data | 2017-02-13 | 2017-02-16 | Assumption that we can use the javascript libraries avaialble. Need to confirm with the TA
| Avinash Singh | yes | Prepare functional requirements Identify the scope of the dashboard | 2017-02-13 | 2017-02-16
| Ashwin Chati | yes | Study existing health dashboards avaialble in public domain Study the sources of their data | 2017-02-13 | 2017-02-16
Next meerting scheduled on 02/16/2017 for the same week
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
2/11/2017 8:00 PM to 8:30 PM | Nikhil Nere | yes | Follow up with TA if we can use An | 2017-02-13 | 2017-02-13 | TA refused to use Angular JS. Only Javascript is to be used for Dashboard implementation Other tasks on track
Agenda: Status on the tasks assigned and discuss if there are any challenges. Assigning next tasks | Ashish Deshpande | yes | Existing set of Tasks | 2017-02-13 |  | On track
| Aditya Kale | yes | Existing set of Tasks | 2017-02-13 |  | On track
| Avinash Singh | yes | Existing set of Tasks | 2017-02-13 |  | On track
| Ashwin Chati | yes | Existing set of Tasks | 2017-02-13 |  | On track

## Week #3
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
2/18/2017 8:00 PM to 8:30 PM | Nikhil Nere | yes | Prepare data tables. Fit data into the requiments Write requirements | 2017-02-20 | 2017-02-24
Agenda: Assign next set of task. Discuss the completion of tasks | Ashish Deshpande | yes | Study the dashboard example shown by the professot and come up with the assignment requirements | 2017-02-20 | 2017-02-24
| Aditya Kale | yes | Create POC Study | 2017-02-20 | 2017-02-24 | Assumption that we can use the javascript libraries avaialble. Need to confirm with the TA
| Avinash Singh | yes | Write requirements and identify use cases | 2017-02-20 | 2017-02-24
| Ashwin Chati | yes | Write requirements and identify use cases Clear doubts with the avaialble datasets and their use as per our design with Professor or TA | 2017-02-20 | 2017-02-24 | Professot cleared doubts about the dataset. Suggested to use and represent data as we want

## Week #4
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
2/25/2017 8:00 PM to 8:30 PM | Nikhil Nere | yes | Complete requirement document Study Graph.org | 2017-02-27 | 2017-03-04
Agenda: Assign next set of task. Discuss the completion of tasks | Ashish Deshpande | yes | Complete Use Cases Study Graph.org | 2017-02-27 | 2017-03-04
| Aditya Kale | yes | Complete Feature list Study Graph.org | 2017-02-27 | 2017-03-04
| Avinash Singh | yes | Complete use cases Study Graph.org | 2017-02-27 | 2017-03-04
| Ashwin Chati | yes | Prepare presentation slides Study Graph.org | 2017-02-27 | 2017-03-04

## Week#5
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
03/04/2017 8:00 PM to 8:30 PM | Nikhil Nere | yes | Designed UI for data selection and display various charts using HTML5 and JavaScript | 2017-03-06
Agenda: Assign next set of task. Discuss the completion of tasks | Ashish Deshpande | yes | Query Data Set to get proper Data using dataframe.js | 2017-03-06
| Aditya Kale | yes | Designed Classes in Java Script using E6 | 2017-03-06
| Avinash Singh | yes | Use chart.js to generate bar graphs - Running example in legacy code. Understand all fields and their functionality | 2017-03-06
| Ashwin Chati | yes | Use chart.js to generate pie charts - Running example in legacy code. Understand all fields and their functionality | 2017-03-06